## 3-Day Agenda
VAVEhub · VE Toolkit
VE Workshop Agenda — 3-Day Template
The six-phase job plan, time-boxed. Adjust durations to complexity; never skip the sequence.
Project / Product: | Team / Facilitator: | Date: | Baseline cost:
Pre-workshop checklist (2–4 weeks before)
✓ | Item | Owner | Due
☐ | Costed BOM validated by finance (material, process, labour, overhead)
☐ | Quality & warranty Pareto for the product
☐ | Competitor samples procured for teardown
☐ | Cross-functional team confirmed (design, mfg, purchasing, quality, finance, supplier)
☐ | Savings target & scope agreed with sponsor
Day 1 · Information + Function Analysis
Time | Phase / activity | Output
09:00–09:30 | Kick-off, scope, targets | Shared goal & ground rules
09:30–11:00 | 1 · Information: cost walk, Pareto, VoC | Validated baseline
11:00–12:30 | Product & competitor teardown (hands-on) | Observations wall
13:30–15:30 | 2 · Function identification (verb–noun) & FAST | FAST diagram
15:30–17:00 | 2 · Function–cost matrix & value index | Ranked mismatches
Day 2 · Creative + Evaluation
Time | Phase / activity | Output
09:00–12:30 | 3 · Creative: brainstorm, 6-3-5, TRIZ, SCAMPER per target function | 200–400 raw ideas, tagged
13:30–15:00 | 4 · Screening: go / grow / park | Shortlist
15:00–17:00 | 4 · Weighted scoring & effort–impact matrix | Top 25–40 ideas with champions
Day 3 · Development + Presentation
Time | Phase / activity | Output
09:00–12:30 | 5 · Development: savings estimate, one-time cost, risk, validation per idea | Draft value proposals
13:30–15:00 | Implementation planning: owners, dates, gates | Roadmap
15:00–16:30 | 6 · Presentation to sponsor / decision board | Go / no-go decisions logged
16:30–17:00 | Wrap: funnel setup, next check-in booked | Live savings funnel
Facilitator rules: defer judgement in Phase 3, and hold to it even with senior people in the room · every idea leaves with a named owner · finance reviews the savings figures before the decision meeting, which can be a week later. Edit times and rows freely to fit your product's complexity.
© Avinash Bhosale · VAVEhub Toolkit — free for personal & internal company use with attribution; commercial redistribution or resale prohibited. Designed & Developed by Avinash Bhosale.